## Content
Document/Tab | Definition | Required for this project?
Executive summary | An executive summary is a brief overview of the project that explains the purpose of the project, the methodology used, the key findings, and the recommendations for improvement. | Yes
Staff&Patient Survey Dashboard | A Patient and staff surveys are an important tool for continuous improvement projects because they provide a direct perspective from the people who are most affected by the process under review. The dashboard provide a summary of this data. | Yes
Value Stream Map | A Value Stream Map provides the entire process flow view from start to finish. It aids in creating plans to optimize the process and helps identify wastes depicted by Kaizen Bursts. | Yes
Time observation sheets (Lead) | Time observation sheets are used to collect data on the amount of time it takes to complete the entire process. This data can then be used to identify areas for improvement, such as reducing waste or bottlenecks. | Yes
Time observation sheets (Cycle) | Time observation sheets are used to collect data on the amount of time it takes an operator to complete his work. This data can then be used to identify areas for improvement, such as reducing waste or bottlenecks. | Yes

## Executive Summary
Executive Summary
The National Performance Target for ED is that 76% of patient should be seen, treated, discharged or admitted within 4 hours from arrival in ED by March 2024. The KGH ED Team have been working with PELC partners, Continuous Improvement Team and other relevant stakeholders, to improve the performance and ensure the right patient is going to the right place at the right time, by implementing a new RAFTING Model. The Team worked tirelessly and demonstrated a real enthusiasm to implement the RAFTING Model in a short time frame, making sure patients would receive the highest quality care in a timely manner. The process was changed and adapted several times throughout the first couple of weeks after implementation, with the team conducting quick PDSA cycles to ensure the best process was running at all times. As a result of this work, the Type 1 performance has improved by 4%, the number of patients waiting 12 hours has reduced, the London Ambulance Service are showing reduced waiting time and 77% of patient feedback was positive about the new process. With regards to the data collected, please see a summary below: 1. Lead Time, the time it takes from when the patient walks into RAFTING to when the patient is discharged or moved out of RAFTING area is: 2h 07min for LAS patients and 1h 52min for PELC patients. 2. Processing Time, the time the process takes without waiting and walking time is: 42min for LAS patients and 37min for PELC patients. 3. Waiting Time, the time the patient is waiting for the next step within the process to happen: 1h 22min for LAS patients and 1h 12min for PELC patients. 4. There are in total 32 improvement opportunities, of these, 44% can be improved with good communication, engagement, preparation, and education. However, while the RAFTING Model has been implemented, there were several challenges noted, with the main themes emerging as follows:  Avoidable process waste  Planning/Staffing Levels  Communication/Education Each of these areas are learning points for future improvement and can be tackled effectively. Following learning from this pilot, key lessons are as follows: 1. Following the Trust Continuous Improvement Methodology which would mitigate avoidable process wastes observed. 2. Greater planning and involvement of all relevant staff groups to mitigate planning and staffing challenges. 3. Wider engagement, communication and education is required to mitigate communication challenges. Our recommendations from the lessons learnt are: 1. Following the Trust Continuous Improvement methodology:  Using the Trust Improvement Methodology would facilitate the planning and preparation for any further changes and preparation for any future pilots.  It would mitigate the avoidable wastes as well as support engagement, communication, and education.  It would facilitate the collection of clear current state metrics, providing a baseline for comparison and indication of success post change.  It would incorporate a ‘learning from others’ approach where similar continuous improvement projects would be reviewed.  It would capture a broader range of improvement ideas.  It would aid in identifying what the most effective method of communication is for each stakeholder, to ensure communication reaches all parties. 2. Greater planning and involvement of all relevant staff groups  Create clearly defined and documented roles and responsibilities.  Clearly identify the proposed process.  Clearly identify upstream and downstream stakeholders.  Create and widely share SOPs.  Create Training. 3. Wider engagement, communication and education required to mitigate communication challenges.  Engaging and involving all relevant stakeholders, both upstream and downstream, before implementing change.  Providing a clear understanding of what is occurring and why.  Enhanced understanding of roles and responsibilities These recommendations would work towards achieving our Trust Annual Goals for 2023-24 alongside meeting the National Performance Target.

## Staff Survey Dashboard
Staff survey
Patient survey
Process rating score (Median) : Neutral

## VSM (full) 24_04_2023
|  |  | v |  | v
| Process Boundaries | [7 empty] | Author: | G.PONZA
From: | Patient enters RAFTING area | [7 empty] | Date prepared:
To: | Patient leaves RAFTING area
| I arrive with the ambulance. |  | I am booked into reception. |  | I am handed over to the consultant and shown where to wait. |  |  | I am assessed by the doctor. |  | My blood is taken. |  | I am assessed by the nurse. |  | I leave RAFTING. |  |  | Wait time median
| Ambulance crew escorts the patient through the RAFTING area with a stretcher or a wheelchair. |  | Receptionist completes patient book in. |  | Paramedic completes patient handover to the doctor in RAFTING providing history of patient's emergency, current observations and any social history relevant to the medical situation. |  |  | The doctor evaluates the patient, asking questions about the accident, past medical history, medications and any social history relevant to the current situation. The patient is physical evaluated if required. A care plan is created and communicated to the patient and other operators. |  | ADA collects bloods if requested by the doctor. They may insert cannula and/or perform ECG if required. |  | The nurse starts the treatment prescribed by the doctor, takes observations and take care of the patient until discharge or transfer to another ward is confirmed. |  | The patient is transferred to another ward by a Porter or is discharged home.
| 2x Paramedic operators |  | 1x Receptionist |  | 1x Doctor |  |  | 1x Doctor |  | 1x ADA |  | 1x Nurse |  | 1xporter
|  | 0:00 |  | 0:13 |  | 0:09 |  |  | 0:13 |  | 0:11 |  | 0:36
| 0:00 |  | 0:02 |  | 0:05 |  |  | 0:02 |  | 0:27 |  | 0:09 |  | 0:00 |  | LAS Totals |  | PELC Totals
[16 empty] | Lead Time | 2:08 | Lead Time | 1:52
CT: | 0:00 | CT: | 0:02 | CT: | 0:05 |  | CT: | 0:02 | CT: | 0:27 |  | 0:09 |  | 0:00 |  | Processing Time | 0:43 | Processing Time | 0:38
PT: | 0:00 | PT: | 0:02 | PT: | 0:05 |  | PT: | 0:02 | PT: | 0:27 |  | 0:06 |  | 0:00 |  | Takt Time (Time Available/Demand) | 0:00 | Takt Time (Time Available/Demand) | 0:00
CO | 0:00 | CO | 0:00 | CO | 0:00 |  | CO | 0:00 | CO | 0:00 |  | 0:00 |  | 0:00 |  | Change Over Time | 0:00 | Change Over Time | 0:00
VA: | 0:00 | VA: | 0:00 | VA: | 0:00 |  | VA: | 0:02 | VA: | 0:09 |  | 0:02 |  | 0:00 |  | Value Added (VA) Time | 0:14 | Value Added (VA) Time | 0:14
NVA: | 0:00 | NVA: | 0:02 | NVA: | 0:05 |  | NVA: | 0:00 | NVA: | 0:18 |  | 0:07 |  | 0:00 |  | Non Value Added (NVA) Time | 1:54 | Non Value Added (NVA) Time | 1:39
%VA: | #DIV/0! | %VA: | 0% | %VA: | 0% |  | %VA: | 100% | %VA: | 32.73% |  | 23.53% |  | 0:00 |  | % VA | 10.59% | % VA | 12%
| I arrive with PELC streamer. |  | I am handed over to the consultant and shown where to wait. |  | I am booked into reception. | [9 empty] | Wait time median
| PELC streamer (1x operators) escorts the patient through the RAFTING area walking or with a wheelchair. |  | PELC streamer completes patient handover to the doctor in RAFTING providing history of patient's emergency, current observations and any social history relevant to the medical situation. |  | Receptionist completes patient book in.
| 1x PELC Streamer operators |  | 1x Doctor |  | 1x Receptionist
|  | 0:01 |  | 0:02
| 0:00 |  | 0:00 |  | 0:02
CT: | 0:00 | CT: | 0:00 | CT: | 0:02
PT: | 0:00 | PT: | 0:00 | PT: | 0:02
CO | 0:00 | CO | 0:00 | CO | 0:00
VA: | 0:00 | VA: | 0:00 | VA: | 0:00
NVA: | 0:00 | NVA: | 0:00 | NVA: | 0:02
%VA: | 0:00 | %VA: | 0% | %VA: | 0%
2
 Current State
Value Stream for: RAFTING
Defect: Printer not working
2
Defect: Staff unsure of process
Defect: Ambulance crew unsure of new process x 2
Defect: Screen not working
Defect: Limited Patient confidentiality and privacy
Defect: Equipment for bloods not available
Defect: Unsure where to place patient
Defect: Patient sent back to PELC
Defect: Duplication in some operators taking obs twice as unaware previously done
Defect: Obs not recorded on VitalPac by Operator who took them - have to be added by another Operator - duplication
Time: Several times patient has to wait between steps in process
1
1
0
1
3
Motion: Doctor walked CT to imaging
Time: Idle time waiting for one ECG Machine
Motion: Patient and staff walking around - unsure where patient should go next
Defect: Patient sent back to PELC
1
1
Defect: Sepsis patient not escalated according to pathway (36min)
Defect: Staff unclear who is doing what
Defect: Blood forms unavailable to bank staff
Defect: Patient placed in incorrect bay/cubicle x 3
Defect: CAS Card misplaced
Defect: Ambulance crew unsure if they could leave
Defect: Patient booked in twice x 2
Time: Multiple huddles to explain/re-explain process
Defect: Patient placed in corridor between peds and Majors B
Defect: CAS Card taken by staff from Majors B
Defect: Triage and Rafting refered as the current process
Defect: PELC patient booked in by 'front' reception - on RAFTING screen but unclear where patient is
Defect: Repeated verbal instrcutions given to & by different staff and variations in instructions - no standards of process
Motion: Staff movement back and forth to find out what is going on
Time: Bottle-neck at booking in and handover from streamer
Defect: No cover / specific instructions to Band 6 to cover NIC on break - desk unmanned
Defect: Unclear what 'tasks' should be happening in which cubicles

## LeadTOF-RAFT
Time Observation Form - Lead Time
Process Boundaries
From | Patient arrives at RAFTING |  | Process |  | KGH RAFTING |  |  | Time Available (mins) |  |  | Date |  |  | 24/04/2023, 26/04/2023
To | Patient leaves RAFTING |  | Cycle |  | RAFTING |  |  | Demand |  |  | Time |  |  | 09:00 - 16:30
Area | KGH ED |  | Operator Title |  | All |  |  | Takt Time (Sec) |  |  | Completed By |  |  | K. Sharifi, G. Ponza and D. Marx
|  |  | Patient Scored >> | YES | YES | YES | YES | YES
Most Frequent Task Time
Step # | Description of Operation | Waste | Waiting/Walking Time (W) / Processing Time (P) | 1 (24/04)(LAS) | 2 (24/04)(LAS) | 3 (26/04)(LAS) | 4 (26/04)(LAS) | 5 (PELC) | Do you want to Include zero values in Mode | Mode | Include zero values in Median | Median | Selected Value (User input required)
1 | Patient arrives at RAFTING with ambulance crew / PELC streamer |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
|  |  | P | 0:00 | 0:00 | 0:05 | 0:00 | 0:02 | YES | 0:00 | YES | 0:00 | Mode
2 | Book in |  |  | 0:00 | 0:00 | 0:05 | 0:00 | 0:02
|  |  | P | 0:00 | 0:00 | 0:03 | 0:00 | 0:00 | NO |  | NO | 0:02 | Median
3 | Patient waits | Time |  | 0:00 | 0:00 | 0:08 | 0:00 | 0:02
|  |  | W | 0:13 | 0:00 | 0:13 | 0:33 | 0:38 | NO | 0:13 | YES |  | Mode
4 | Ambulance crew hand over to Consultant |  |  | 0:13 | 0:00 | 0:21 | 0:33 | 0:40
|  |  | P | 0:03 | 0:00 | 0:05 | 0:08 | 0:00 | NO |  | NO | 0:05 | Median
5 | Patient waits |  |  | 0:16 | 0:00 | 0:26 | 0:41 | 0:40
|  |  | W | 0:14 | 0:00 | 0:06 | 0:09 | 0:00 | NO |  | NO | 0:09 | Median
6 | Patient assessed / seen by Doctor |  |  | 0:30 | 0:00 | 0:32 | 0:50 | 0:40
|  |  | P | 0:00 | 0:07 | 0:02 | 0:03 | 0:01 | NO |  | NO | 0:02 | Median
7 | Patient waits | Time |  | 0:30 | 0:07 | 0:34 | 0:53 | 0:41
|  |  | W | 0:04 | 0:18 | 0:08 | 0:00 | 0:28 | NO |  | NO | 0:13 | Median
8 | Patient's blood taken by ADA |  |  | 0:34 | 0:25 | 0:42 | 0:53 | 1:08
|  |  | P | 0:14 | 0:10 | 0:00 | 0:00 | 0:12 | NO |  | NO | 0:12 | Median
9 | Patient waits | Time |  | 0:48 | 0:35 | 0:42 | 0:53 | 1:20
|  |  | W | 0:00 | 0:18 | 0:00 | 0:00 | 0:05 | NO |  | NO | 0:11 | Median
10 | Patient assessed or treated by Nurse |  |  | 0:48 | 0:53 | 0:42 | 0:53 | 1:25
|  |  | P | 0:12 | 0:26 | 0:02 | 0:08 | 0:00 | NO |  | YES | 0:08 | Median
11 | Patient waits | Time |  | 1:01 | 1:19 | 0:44 | 1:01 | 1:25
|  |  | W | 0:00 | 0:00 | 0:55 | 0:17 | 0:00 | NO |  | NO | 0:36 | Median
12 | END |  |  | 1:01 | 1:19 | 0:02 | 1:18 | 1:25
| Time For One Observation |  |  | 1:00 | 1:19 | 1:39 | 1:18 | 1:25 |  |  |  | 1:51
| Minus Walking/Wait Time | W |  | 0:31 | 0:36 | 1:22 | 0:59 | 1:11 |  |  |  | 1:22
| .= Processing Time | P |  | 0:29 | 0:43 | 0:17 | 0:19 | 0:14 |  |  |  | 0:29
RESET SHEET TO TEMPLATE

## CycleTOF-PELC Streamer (26-04)
Time Observation Form - Cycle Time
Process Boundaries
From | Streamer arrives with patient |  | Process |  | KGH RAFTING |  |  | Time Available (mins) |  |  | Date |  | 2023-04-26
To | Streamer leaves and booking in ends |  | Cycle |  | Streamer Handover to RAFTING |  |  | Demand |  |  | Time |  | 09:30-12:30
Area | KGH ED - RAFTING |  | Operator Title |  | Streamer, Doctor, Receptionist |  |  | Takt Time (Sec) |  |  | Completed By |  | D. Marx
|  |  | Patient Scored >> | YES | YES | YES | YES
Most Frequent Task Time
Step # | Description of Operation | Waste | Waiting Time (W) / Processing Time (P) | 1 | 2 | 3 | 4 | Include zero values in Mode | Mode | Include zero values in Median | Median | Selected Value (User input required)
1 | Strearmer arrives with patient |  |  | 0:00 | 0:00 | 0:00 | 0:00
|  |  | P | 0:00 | 0:00 | 0:00 | 0:00 | NO |  | NO |  | Median
2 | Streamer waits | Time |  | 0:00 | 0:00 | 0:00 | 0:00
|  |  | w | 0:00 | 0:05 | 0:00 | 0:01 | YES |  | YES | 0:01 | Median
3 | Receptionist books in - demographics questions |  |  | 0:00 | 0:05 | 0:00 | 0:01
|  |  | P | 0:01 | 0:00 | 0:00 | 0:00 | NO |  | NO | 0:01 | Median
4 | Receptionist books in - presenting complaint details |  |  | 0:01 | 0:05 | 0:00 | 0:01
|  |  | P | 0:00 | 0:00 | 0:00 | 0:00 | NO |  | NO | 0:00 | Median
5 | Receptionist books in - duration of presenting complaint |  |  | 0:01 | 0:05 | 0:00 | 0:01
|  |  | P | 0:00 | 0:00 | 0:00 | 0:00 | NO |  | NO | 0:00 | Median
6 | Receptionist books in - mode of transport |  |  | 0:02 | 0:05 | 0:00 | 0:01
|  |  | P | 0:00 | 0:00 | 0:00 | 0:00 | NO |  | NO | 0:00 | Median
7 | Receptionist books in - time of arrival |  |  | 0:02 | 0:05 | 0:00 | 0:01
|  |  | P | 0:00 | 0:00 | 0:00 | 0:00 | NO |  | NO | 0:00 | Median
8 | Streamer waits | Time |  | 0:02 | 0:05 | 0:00 | 0:01
|  |  | w | 0:02 | 0:00 | 0:00 | 0:00 | NO |  | NO | 0:02 | Median
9 | Handover taken by NEFLT DR / ED LEAD DR |  |  | 0:04 | 0:05 | 0:00 | 0:01
|  |  | P | 0:00 | 0:00 | 0:00 | 0:00 | NO |  | NO | 0:00 | Median
10 | End: Streamer leaves |  |  | 0:04 | 0:05 | 0:00 | 0:01
|  |  | P |  | 0:00 | 0:00 | 0:00 | NO |  | NO |  | Median
11 | Patient waits | Time |  |  | 0:05 | 0:00 | 0:01
|  |  | w |  | 0:01 | 0:00 | 0:00 | NO |  | NO | 0:00 | Median
12 | Doctor gives form to Receptionist |  |  |  | 0:06 | 0:00 | 0:02
|  |  | P |  | 0:00 | 0:00 | 0:00 | NO |  | NO |  | Median
13 | Patient waits | Time |  |  | 0:06 | 0:00 | 0:02
|  |  | w |  | 0:06 | 0:02 | 0:00 | NO |  | NO | 0:04 | Median
14 | Receptionist books in |  |  |  | 0:11 | 0:03 | 0:02
|  |  | P |  | 0:04 | 0:01 | 0:00 | NO |  | NO | 0:02 | Median
15 | End: Book in ends |  |  |  | 0:15 | 0:03 | 0:02
| Time For One Observation |  |  | 0:04 | 0:15 | 0:03 | 0:02 |  |  |  | 0:11
| Minus Walking/Wait Time | W |  | 0:02 | 0:11 | 0:03 | 0:02 |  |  |  | 0:07
| .= Processing Time | P |  | 0:02 | 0:04 | 0:01 | 0:00 |  |  |  | 0:04

## Time Ob (CT receptionist)
Time Observation Form - Cycle Time Receptionist
Process Boundaries
From | Patient arrives |  | Process |  | Check-in |  |  | Time Available (mins) |  |  | Date
To | Patient's registration is completed |  | Cycle |  | Receptionist |  |  | Demand |  |  | Time
Area | RAFT KGH ED |  | Operator Title |  | Receptionist |  |  | Takt Time (Sec) |  |  | Completed By |  | G.PONZA
Most Frequent Task Time
Step # | Description of Operation | Waste | Waiting Time (W) / Processing Time (P) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Mode | Median | Selected Value (User input required)
1 | patient arrives |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
|  |  | p | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 |  | 0:00 | Median
2 | Patient's ID look into the system |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
|  |  | p | 0:01 | 0:00 | 0:00 | 0:00 | 0:01 | 0:00 | 0:00 |  | 0:00 | Median
3 | Patient's emergency contact are checked |  |  | 0:01 | 0:01 | 0:01 | 0:00 | 0:01 | 0:00 | 0:00
|  |  | p | 0:01 | 0:00 | 0:01 | 0:00 | 0:01 | 0:01 | 0:02 |  | 0:01 | Median
4 | Patient's transport checked |  |  | 0:02 | 0:01 | 0:02 | 0:01 | 0:02 | 0:02 | 0:02
|  |  | p | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:01 |  | 0:00 | Median
5 | Patient's symptoms recorded |  |  | 0:02 | 0:01 | 0:02 | 0:01 | 0:02 | 0:02 | 0:03
|  |  | p | 0:00 | 0:01 | 0:00 | 0:00 | 0:00 | 0:00 | 0:02 |  | 0:00 | Median
6 | Registration completed |  |  | 0:02 | 0:02 | 0:02 | 0:01 | 0:02 | 0:02 | 0:05
|  |  | p | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:05 | 0:00 | 0:00 | Median
7 | END |  |  | 0:02 | 0:02 | 0:02 | 0:02 | 0:02 | 0:02 | 0:00
Median
| Time For One Observation |  |  | 0:02 | 0:02 | 0:02 | 0:02 | 0:02 | 0:02 | 0:11 |  | 0:02
| Minus Walking/Wait Time | W |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 |  | 0:00
| .= Processing Time | P |  | 0:02 | 0:02 | 0:02 | 0:02 | 0:02 | 0:02 | 0:11 |  | 0:02

## Time Ob (ADA CT) 05_05_23
Time Observation Form - Cycle Time
Process Boundaries
From | Identify next patient for blood test and/or ECG |  | Process |  | ADA carries out blood test and/or ECG |  |  | Time Available (mins) |  |  | Date |  | 2023-05-05
To | Blood test and/or ECG completed for patient |  | Cycle |  | ADA |  |  | Demand |  |  | Time |  | 09:00 - 12:00
Area | KGH ED |  | Operator Title |  | ADA |  |  | Takt Time (Sec) |  |  | Completed By |  | Neha
Most Frequent Task Time
Step # | Description of Operation | Waste | Waiting Time (W) / Processing Time (P) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Mode | Median | Selected Value (User input required)
1 | Find next patient in Careflow and print patient paperwork |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
|  |  | P | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:02 | 0:03 |  | 0:02 | Median
2 | Prepare blood test tray |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:02 | 0:03
|  |  | P | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:03 | 0:01 |  | 0:02 | Median
3 | Call patient to ADA room |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:05 | 0:04
|  |  | P | 0:03 | 0:00 | 0:00 | 0:00 | 0:00 | 0:04 | 0:06 |  | 0:04 | Median
4 | Do blood test |  |  | 0:03 | 0:00 | 0:00 | 0:00 | 0:00 | 0:09 | 0:10
|  |  | P | 0:06 | 0:06 | 0:03 | 0:04 | 0:05 | 0:03 | 0:04 |  | 0:04 | Median
5 | Do ECG |  |  | 0:00 | 0:06 | 0:03 | 0:04 | 0:05 | 0:12 | 0:14
|  |  | P | 0:00 | 0:05 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:05 |  | Mode
4 | Label & bag samples. Do blood gas test. |  |  | 0:09 | 0:11 | 0:03 | 0:04 | 0:05 | 0:12 | 0:14
|  |  | P | 0:03 | 0:05 | 0:05 | 0:08 | 0:07 | 0:04 | 0:04 | 0:04 | 0:05 | Median
6 | Take blood gas and /or ECG results to doctor |  |  | 0:12 | 0:16 | 0:08 | 0:12 | 0:12 | 0:16 | 0:18
|  |  | P | 0:01 | 0:02 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 |  | 0:02 | Median
7 | Take sample to POD machine |  |  | 0:13 | 0:18 | 0:08 | 0:12 | 0:12 | 0:16 | 0:18
|  |  | P | 0:01 | 0:06 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 |  | 0:04 | Median
8 | End |  |  | 0:14 | 0:24 | 0:08 | 0:12 | 0:12 | 0:16 | 0:18
| Time For One Observation |  |  | 0:14 | 0:24 | 0:08 | 0:12 | 0:12 | 0:16 | 0:18 |  | 0:27
| Minus Walking/Wait Time | W |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 |  | 0:00
| .= Processing Time | P |  | 0:14 | 0:24 | 0:08 | 0:12 | 0:12 | 0:16 | 0:18 |  | 0:27

## Time Ob (Nurse CT) 09_05_23
Time Observation Form - Cycle Time
Process Boundaries
From | Nurse Allocated Patient |  | Process |  | Nurse rafting |  |  | Time Available (mins) |  |  | Date |  | 2023-05-09
To | Nurse finishes with patient |  | Cycle |  | Nurse |  |  | Demand |  |  | Time |  | 12:00-16:00
Area | KGH ED |  | Operator Title |  | Nurse |  |  | Takt Time (Sec) |  |  | Completed By |  | Lara + Grace
Most Frequent Task Time
Step # | Description of Operation | Waste | Waiting Time (W) / Processing Time (P) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Mode | Median | Selected Value (User input required)
1 | Nurse allocated to patient |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
|  |  | P | 0:00 | 0:02 | 0:03 | 0:01 | 0:00 | 0:02 |  | 0:00 |  | Mode
2 | Nurse reviews notes |  |  | 0:00 | 0:02 | 0:03 | 0:01 | 0:00 | 0:02
|  |  | P | 0:04 |  | 0:03 | 0:01 | 0:03 | 0:01 |  |  | 0:03 | Median
3 | Nurse attends and does obs |  |  | 0:04 | 0:02 | 0:06 | 0:02 | 0:03 | 0:03
|  |  | P | 1: 0:10; 3: 0:02; 4: 0:02 | 0:02 |  | Mode
4 | Nurse takes patient to waiting area |  |  | 0:14 | 0:02 | 0:08 | 0:04 | 0:03 | 0:03
|  |  | W | 5: 0:01; 6: 0:04 |  | 0:02 | Median
5 | Nurse updates notes |  |  | 0:14 | 0:02 | 0:08 | 0:04 | 0:04 | 0:07
|  |  | P | 2: 0:06; 4: 0:01; 5: 0:01 | 0:01 |  | Mode
4 | End |  |  | 0:14 | 0:08 | 0:08 | 0:05 | 0:05 | 0:07
| Time For One Observation |  |  | 0:14 | 0:08 | 0:08 | 0:05 | 0:05 | 0:07 | 0:00 |  | 0:09
| Minus Walking/Wait Time | W |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:01 | 0:04 | 0:00 |  | 0:02
| .= Processing Time | P |  | 0:14 | 0:08 | 0:08 | 0:05 | 0:04 | 0:03 | 0:00 |  | 0:06

## Staff Feedback Survey Data (hidden)
No | Date | Role | Q1: How would you rate the new process from 1 - 5? | Why? | Q1: How would you rate the new process from 1 - 5 Themed | Q2: Have you been clearly communicated what you should be doing? | Comments | Q2: Have you been clearly communicated what you should be doing? Themed | Q3: If you could describe this process in a word, what would you choose? | Q3: If you could describe this process in a word, what would you choose? Themed | Q4: If you could change anything, what would you change? | Q4: If you could change anything, what would you change? Themed | Q4: If you could change anything, what would you change? High Themed | Q5: What do you think should have been done better?
1 | 2023-05-11 | ADA | 2 | ADA not sure how to prioritise who is next in the queue, they can only look at presentation e.g. chest pain. Notes difficult to locate. Patients difficult to locate. | Hard to prioritise | No | There should have been meetings before with everyone involved. Maybe used role play to demonstrate the new process. Concerns about safety to access Resus if patient collapses in Rafting as corridor often blocked by waiting LAS. | Communication needs improving | Terrible | Poor | Area is too packed - need more space or change of structure/rooms. Communication needs to be improved of location of CAS Card / Patient notes. | More space | Planning | Trial with all staff before making changes. Better communication about roles.
2 | 2023-05-11 | Receptionist | 2 | Ambulance checking in at front leaves 1 x crew member alone with patient. Privacy in Rafting is a problem. Confidentiality is a problem with patient papers left on Rafting desk in view of those checking in. | Privacy issues | Yes | Brief email sent. If unsure will check with colleague as infrequent shifts at KGH. | Communication needs improving | Crap | Poor | Order at desk - distracting for clinicians if receptionist talking to patients to book in. Queens has more private reception setup with mini 'cubicle'. Difficult to deal with interruptions at either desk as now only 1 x receptionist at each who is busy with patient/LAS. | Busy at the desk | Planning | Red line at desk to queue behind and wait to be called forward?
3 | 2023-05-11 | Receptionist | 3 | Good for the patients but limited work for Receptionist at Rafting desk | Limited work | Yes |  |  | Smooth | Poor | Rafting Receptionist has limited tasks at Rafting desk - could these be done at front desk? Rafting desk space could then be used for clinicians. | Increase work for Rafting Receptionist | Planning | Planning of how to use the space available. Difficult to track where patients are in main waiting area as there are patients from different areas (Rafting, Majors B etc.)
4 | 2023-05-11 | Doctor | 3 | Depends on the pressure on the day, it is inconsistent | Pressure dependent | Yes |  |  | Evolving | Constant process changes | More Staff and better skill mix. 2 x Senior Doctors at all times. Problems arise especially after 6pm. | More Staff | Staffing levels | People doing the work need to be involved in planning as they will know the details of what happens on the floor.
5 | 2023-05-11 | Nurse | 3 | Fewer patients today and it is still early. | Good day today | Yes | Today the Rafting team all met to make it clear who is doing what. Doctors are writing in the Narrative on Careflow what next steps should be so they don't have to do verbal handover for Nurse - this saves time when very busy. | Constant process changes | Last week = Chaotic Now = Organised | Constant process changes | I like the new changes. | Nothing | Nothing | Planning should have been done early. Good flow in other areas is helping today. 4 cubicles for Rafting.
6 | 2023-05-11 | ADA | 3 | Waiting area is crowded. | Long Patient wait time | Yes |  |  | Learning (when learning to walk a child will always fall down a few times) | Constant process changes | Separate PELC/Walk in from Rafting - use all rooms at front for PELC/Walk in and everything on other side of double door for Rafting. Use HCA cubicle in main waiting area for Doctor or something else. | Space allocation | Planning
7 | 2023-05-11 | Doctor | 3 | 8am - 6pm is fine. After 6pm you still need 2 x Senior Doctors Rafting if you want it running 24/7. Education should be better for roles (Nurses and Doctors). Flow has a big impact. | Communication needs improving | Yes | Could have been better. | Communication needs improving | Working | Working | More Staff. Better flow. | More Staff | Staffing levels | Done well.
8 | 2023-05-11 | Nurse | 4 | Today is a good day, few patients. | Pressure dependent | Yes |  |  | Fabulous | Working | More Doctors so they can do faster Rafting | More Staff | Staffing levels | More space required for the process
9 | 2023-05-11 | Nurse | 4 | Process is new again today | Constant process changes | Yes |  |  | Perfect | Working | Nothing | Nothing | Nothing | Ok for now
10 | 2023-05-11 | ADA | 4 | I love change. | Good day today | Yes | Instructions are now clear but it would be helpful if when staff are told information in huddles they could also be 'shown' on the floor and then later they can do a check in to see if staff on the floor are following the instructions that were given. | Communication needs improving | New | Working | More computers for ADAs - 3 x ADAs with 1 x computer - have to wait for each other. | More computers | Planning | Someone to follow-up and come see if the instructions given are being managed on the floor and the process is going to plan.
11 | 2023-05-11 | Nurse | 4 | Good for patients. OK for staff. | Good day today | Yes | If unsure I will speak to a Senior. | Communication needs improving | Life Changing | Working | Reduce the queue. | Improve flow | Planning | Doctors should be more clear.
12 | 2023-05-11 | Nurse | 5 | Good for patients. Some confusion for staff. Sometimes Doctors send patients to another area but you don't know where. | Communication needs improving | Yes | It helped when Matron came to explain today in morning handover. Before than it was not clear. | Communication needs improving | Brilliant (will be good for Sepsis patients to get it all at once) | Working | Communications about who has been Rafted and what jobs need to be done. | SOP | Communication | Triage skills are being taken away from the Nurses. How can they maintain these/similar skills?
13 | 2023-05-15 | Doctor | 5 |  |  | YES |  | Patient safety concerns |  |  | Space and Team allocated | Space allocation | Planning | Virtual and PELC over see their activity
14 | 2023-05-15 | Receptionist | 2.5/3 | Having pt sharing personl info and waiting in cubical. No sense of privacy esp. for DV or Sexual abuse | Privacy issues | Yes |  | Communication needs improving | Well Organised / Carnage | Working | Cubicals for Privacy | Privacy | Planning | Change was too sudden. Needed more time to adjust the setting and organise. Receptionist now using the Pc and team have lost clinical space.
15 | 2023-05-15 | ADA | 4 | Last little bit was confusing with the A&E Cards | Communication needs improving | Yes |  | Communication needs improving | Streamline | Working | Nurses to do ECGs and let us know if Pt needs cannula (not always told) | Staff allocation | Planning | Pod Shoot for bloods closer.
16 | 2023-05-15 | ADA | 4 | A lot easier but still a little bit of a mess | Constant process changes | Yes |  | Communication needs improving | Alright | Working | A bit smoother. Stop Pt in corridors | Better flow | Planning
17 | 2023-05-16 | Nurse | 4 | Better than the old, but needs polishing | Good day today | No |  |  | Getting There | Working | More Staff | More staff | Staffing levels | We have it now with the allocation of tasks
18 |  | no.1 Q4 comment split out | [9 empty] | Communication | Communication
19 |  | no.1 Q4 comment split out | [9 empty] | Required documents/equipment available at point of use | Planning
20 |  | no.2 Q4 comment split out | [9 empty] | Different use of space | Planning
21 |  | no.2 Q4 comment split out | [9 empty] | More Staff | Staffing levels
22 |  | no.3 Q4 comment split out | [9 empty] | Different use of space | Planning
23 |  | no.4 Q4 comment split out | [9 empty] | Increase skill mix | Planning
24 |  | no. 7 Q4 comment split out | [9 empty] | Improve flow | Planning
25 |  | no.13 Q4 comment split out | [9 empty] | More Staff | Staffing levels
26 |  | no.15 Q4 comment split out | [9 empty] | Communication | Communication
27 |  | no.1 Q5 comments split out | [9 empty] | Simulations | Planning
28 |  | no.1 Q5 comments split out | [9 empty] | Communication | Communication
29 |  | no.2 Q5 comments split out | [9 empty] | Queue processing | Planning
30 |  | no.3 Q5 comments split out | [9 empty] | Space allocation | Planning
31 |  | no.5 Q5 comments split out | [9 empty] | Better planning | Planning
32 |  | no.7 Q5 comments split out | [9 empty] | Nothing | Nothing
33 |  | no.8 Q5 comments split out | [9 empty] | More space | Planning
34 |  | no.9 Q5 comments split out | [9 empty] | Nothing | Nothing
35 |  | no.10 Q5 comments split out | [9 empty] | Leadership oversight | Planning
36 |  | no.11 Q5 comments split out | [9 empty] | SOP | Communication
37 |  | no.12 Q5 comments split out | [9 empty] | Nurse Triage Skill lost | Nurse Triage Skill lost
38 |  | no.13 Q5 comments split out | [9 empty] | SOP | Communication
39 |  | no.14 Q5 comments split out | [9 empty] | Planning | Planning
40 |  | no.15 Q5 comments split out | [9 empty] | Blood shoot nearer | Planning
41 |  | no.16 Q5 comments split out | [9 empty] | More Staff | Staffing levels
42 |  | no.16 Q5 comments split out | [9 empty] | Planning | Planning
|  | no.17 Q5 comments split out | [9 empty] | Nothing | Nothing

## Staff Survey pivot table (hidden)
Process rating. (Median) | [5 empty] | Process rating reason |  |  |  | Understanding your role. |  |  |  | Describe Process in one word. |  |  |  | What would you change? |  | What would you change/Improve?
[6 empty] | Total | 16 |  |  | Total | 11 |  |  | Total | 16 |  |  |  |  | Total | 42
Role | Q1: How would you rate the new process from 1 - 5? | (empty) |  |  |  | Q1: How would you rate the new process from 1 - 5 Themed | Count of No |  |  | Q2: Have you been clearly communicated what you should be doing? Themed | Count of No |  |  | Q3: If you could describe this process in a word, what would you choose? Themed | Count of No |  |  | Q4: If you could change anything, what would you change? Themed | Count of No | Q4: If you could change anything, what would you change? High Themed | Count of No
ADA | 2 |  | Role | Process rating. | Process Median | Communication needs improving | 3 |  |  | Communication needs improving | 9 |  |  | Constant process changes | 3 |  |  | Increase work for Rafting Receptionist | 1 | Communication | 6
| 3 |  | ADA | 2 | 3 | Constant process changes | 2 | Communication needs improving | 18.75% | Constant process changes | 1 | Communication needs improving | 81.82% | Poor | 3 |  |  | More computers | 1 | Nothing | 4 | Communication | 14.29%
| 4 |  | ADA | 4 |  | Good day today | 4 | Constant process changes | 25% | Patient safety concerns | 1 | Constant process changes | 9.091% | Working | 10 | Poor | 37.5% | More Staff | 7 | Nurse Triage Skill lost | 1 | Nothing | 2.381%
Doctor | 3 |  | ADA | 3 |  | Hard to prioritise | 1 | Good day today | 6.25% |  |  | Patient safety concerns | 9.091% |  |  | Working | 62.5% | Communication | 3 | Planning | 24 | Nurse Triage Skill lost | 57.14%
| 5 |  | Doctor | 5 |  | Limited work | 1 | Hard to prioritise | 6.25% | [8 empty] | More space | 2 | Staffing levels | 7 | Planning | 16.67%
Nurse | 3 |  | Doctor | 3 |  | Long Patient wait time | 1 | Limited work | 6.25% | [8 empty] | Required documents/equipment available at point of use | 1 | (empty) |  | Staffing levels | 0%
| 4 |  | Nurse | 4 |  | Pressure dependent | 2 | Long Patient wait time | 12.5% | [8 empty] | Nothing | 2
| 5 |  | Nurse | 5 |  | Privacy issues | 2 | Pressure dependent | 12.5% | [8 empty] | Planning | 2
Receptionist | 2 |  | Nurse | 2 |  |  |  | Privacy issues | 0% | [8 empty] | Queue processing | 1
| 3 |  | Receptionist | 3 | [13 empty] | Busy at the desk | 1
| 2.5/3 |  | Receptionist | 2.5/3 | [13 empty] | Space allocation | 3
Total Result |  |  | Receptionist | 3 | [13 empty] | Nothing | 2
[18 empty] | SOP | 3
[18 empty] | Privacy | 1
[18 empty] | Staff allocation | 1
[18 empty] | Better flow | 1
[18 empty] | Different use of space | 2
[18 empty] | Increase skill mix | 1
[18 empty] | Improve flow | 2
[18 empty] | Simulations | 1
[18 empty] | Better planning | 1
[18 empty] | Leadership oversight | 1
[18 empty] | Nurse Triage Skill lost | 1
[18 empty] | Blood shoot nearer | 1
[18 empty] | Total Result | 42

## Patient Survey data (hidden)
No | Date | Patient | Q1: Did you receive good care today? If no, specify the reason why | Why? | Q2: Have you been clearly communicated what your plan was? | Q2: Have you been clearly communicated what your plan was? (One Word) | Q3: If you could describe this process in a word, what would you choose? | Q3: If you could describe this process in a word, what would you choose? Themed | Q4: If you could change anything, what would you change? | Q4: If you could change anything, what would you change? Themed
1 | 2023-05-15 | Patient | Yes |  | No | No | Excellent | Excellent | Nothing, very good so far. | Nothing
2 | 2023-05-15 | Patient | Yes |  | Yes, waiting for tests | Yes | Excellent | Excellent | Nothing | Nothing
3 | 2023-05-15 | Patient | Yes |  | Yes | Yes | Excellent | Excellent | No | Nothing
4 | 2023-05-15 | Patient | Yes |  | Yes, explained what was happening, but unsure of what is next. | Yes | Sufficient. Saw 8 people in 2 hours! | Sufficient | Staff member was rude on arrival and shouted "Sit Down" like you would to a child. Then they felt bad and came back and moved me to another area. | Staff Behaviour
5 | 2023-05-15 | Patient | Yes |  | Yes, clearly | Yes | Very Good | Good | No | Nothing
6 | 2023-05-15 | Patient | Yes |  | No | No | Curt, info wasn't forthcoming. Staff not recognising the need for information. Simple steps. Give as much info as possible. Blood test area pretty good. Lady was good. | Poor | Communication | Communication
7 | 2023-05-15 | Patient | Yes |  | Not really, unsure what's next. | No | Supportive | Good | Speed | Speed
8 | 2023-05-15 | Patient | Yes |  | Yes | Yes | Efficient | Good | More Comfortable Trolly | Trolly
9 | 2023-05-15 | Patient | Yes |  | Yes | Yes | Good | Good | No | Nothing

## Patient Survey pivot tables (hidden)
Total | 9 |  |  | Total | 9 |  |  | Total | 9 |  |  | Total | 9
Q1: Did you receive good care today? If no, specify the reason why | Count of Patient | Did you recieve good care today? |  | Q2: Have you been clearly communicated what your plan was? (One Word) | Count of Patient | Did you recieve good care today? |  | Q3: If you could describe this process in a word, what would you choose? Themed | Count of Patient | Did you recieve good care today? |  | Q4: If you could change anything, what would you change? Themed | Count of Patient | Did you recieve good care today?
Yes | 9 |  | Did you recieve good care today? | No | 3 |  |  | Excellent | 3 |  |  | Communication | 1
|  | Yes | 100% | Yes | 6 | No | 33.33% | Good | 4 | Excellent | 33.33% | Nothing | 5 | Communication | 11.11%
|  |  |  | (empty) |  | Yes | 66.67% | Poor | 1 | Good | 11.11% | Speed | 1 | Nothing | 11.11%
[8 empty] | Sufficient | 1 | Poor | 11.11% | Staff Behaviour | 1 | Speed | 11.11%
[8 empty] | (empty) |  | Sufficient | 0% | Trolly | 1 | Staff Behaviour | 11.11%
[12 empty] | (empty) |  | Trolly | 0%
Did you recieve good care today?
Was your plan communicated clearly?
Was your plan communicated clearly?
Was your plan communicated clearly?